## Enity Structure
Oganisation Structure
HO
|  |  | 1 | Department A1
HO@bhumati.com
CentreA |  |  |  |  | Centre B
1 | Department A1 |  |  |  | 1 | Department B1
| 1 | centreA@bhumati.com |  |  |  | 1 | employeeB1-01@bhumati.com
| 2 | employeeA1-01@bhumati.com |  |  |  | 2 | employeeB1-02@bhumati.com
| 3 | employeeA1-02@bhumati.com |  |  |  | 3 | employeeB1-03@bhumati.com
| 4 | employeeA1-03@bhumati.com
2 | Department A2
employeeA2-01@bhumati.com
employeeA2-02@bhumati.com
employeeA2-03@bhumati.com
Online leave flow
3 | Department A3

## Flow
Online leave flow
Centre A
Department A1 |  | Centre A
centreA@bhumati.com |  | Department A2
employeeA1-01@bhumati.com |  | employeeA2-01@bhumati.com
employeeA2-02@bhumati.com
employeeA1-02@bhumati.com |  | employeeA2-03@bhumati.com
employeeA1-03@bhumati.com
Applicant |  | First Approver | Second Approver
A1-02 |  | A1-01 | Centre@bhumati
A1-03 |  | A1-01 | Centre@bhumati

## Sheet3
Leave Master |  | Level | Combination | Days | Start Date | End Date | Status
1 | Leave Type | 2 | Listing+Add | 2 | 2019-06-01 | 2019-08-01 | Completed
2 | Manage Leave Document | 3 | List+add+edit | 2 | 2019-08-01 | 2019-10-01 | Completed
7 | Leave Session | 3 | L+A+E | 2 | 2019-10-01 | 2019-12-01 | Completed
8 | Leave Rules | 3 |  | 3 | 13/1/2019 | 13/1/2019 | Completed
3 | Apply Document To Leave Rule | 2 | List+Add | 2 | 14/1/2019 | 15/1/2019 | Completed
4 | Shift Master | 4 |  | 3 | 16/1/2019 | 17/1/2019 | Completed
5 | Centre wise shift Allocation | 2 |  | 2 | 18/1/2019 | 19/1/2019 | Completed
6 | Shift Allocation | 2 |  | 2 | 20/1/2019 | 22/1/2019 | Completed
9 | Leave Rule applicable Details | 3 |  | 3 | 23/1/2019 | 24/1/2019 | Completed
10 | Leave Post Manual | 2 |  | 3 | 25/1/2019 | 27/1/2019 | Completed
11 | Leave Rule Exempted Employee | 3 |  | 3 | 28/1/2019 | 28/1/2019 | Completed
12 | Leave Late Mark Rules Details | 2 |  | 3 | 29/1/2019 | 29/1/2019 | Completed
13 | Add Task Details | 2 | Listing+Add | 2 |  |  |  | Need to Confirm
Transaction
1 | Manual attendance | 3 |  | 4 |  |  |  | DB intergration and Testing Pending
2 | Attendance Special Request | 3 |  | 4
3 | Leave Application Cancel | 3 |  | 4
4 | Compensatory Off Day Application | 3 |  | 4
5 | Leave Application Report | 2 |  | 4
6 | Leave Application Status Report | 2 |  | 4
7 | Leave Application Self | 3 |  | 4 |  |  |  | DB intergration and Testing Pending
8 | Leave Year end | 3 |  | 4
64